{"text_format":"3","workbook":"xls","n_sheets":4,"sheets":["预算审查作业流程","标准","预算清单","拟建预算审查报告"],"not_rendered":{"external_links":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"预算审查作业流程","index":0,"n_rows":18,"n_cols":8,"rows_kept":18,"merged":[[0,0,1,1],[0,2,1,3],[2,0,3,1],[2,7,3,7],[4,0,16,0],[17,0,17,1],[17,2,17,7]],"flags":["formulas_cached_only"]}
["标题",null,"10万元以上工程预算审查审批流程",null,"类别","级别","流程主人","公司/部门"]
[{"$nulls":4},"预算/采购管理","一级","集团预算采购高级主管","集团公司"]
[" 组织单元",null,"成员企业CEO","成员企业工程项目负责人","集团计财部长","集团预算采购高级主管"," 集团预算采购主管","责任职位"]
[null,null,"A","B","C","D","E"]
["管\n理\n动\n作",1,{"$nulls":5},"D1：预算采购高级主管"]
[null,2,{"$nulls":5},"B2：成员企业工程负责人"]
[null,3,{"$nulls":5},"D3：预算高级主管"]
[null,4,{"$nulls":5},"D4：预算高级主管"]
[null,5,{"$nulls":5},"E5：预算采购主管"]
[null,6,{"$nulls":5},"E6：预算采购主管"]
[null,7,{"$nulls":5},"C7：集团计财部长\nD7：预算采购主管"]
[null,8,{"$nulls":5},"B8：成员企业工程负责人A8:成员企业CEO"]
[null,9,{"$nulls":5},"D9:预算 采购高级主管"]
[null,10,{"$nulls":5},"C10:集团计财部长"]
[null,11,{"$nulls":5},"C11：集团计财部长"]
[null,12,{"$nulls":5},"B12:工程负责人                         D12:预算采购高级主管"]
[null,13,{"$nulls":5},"D13：预算采购高级主管"]
["作用",null,"准确核定拟建工程造价,控制工程成本"]

{"sheet":"标准","index":1,"n_rows":19,"n_cols":8,"rows_kept":19,"merged":[[0,0,1,0],[0,1,1,3],[2,0,2,1]],"flags":["formulas_cached_only"]}
["标题","10万元以上工程预算审查审批流程",null,null,"类别","级别","流程主人","公司/部门"]
[{"$nulls":4},"预算/采购管理","一级","集团预算采购高级主管","集团公司"]
["任务名称",null,"节点","标准作业程序及重点（流程细化）","作业标准（量化）","运作凭证","责任人","闸口"]
[1,"开始","D1",{"$nulls":3},"集团预算采购高级主管"]
[2,"预算报审","B2","集团成员企业在建筑工程开工前,收集整理其他有关预算算资料提交集团计财部预算采购小组审核","成员企业在建筑工程开工前60天内,建筑工程预算及相关资料向集团报审",null,"成员企业工程负责人"]
[3,"完整性审查","D3","集团预算采购高级主管根椐拟建工程预算要求审核成员企业工程负责人提交的拟建工程资料的完整性.","收到拟建工程预算资料后1个工作日审核完毕",null,"集团预算采购高级主管"]
[4,"编制审查计划","D4","集团预算采购高级主管根据部门工作编制审查工作计划","根据部门工作计划统一调整编制1个工作日编制完毕",null,"集团预算采购高级主管"]
[5,"专业审查","E5","集团专业预算采购主管根据成员企业工程负责人提交的施工合同、施工图纸、设计变更、施工图预算书、甲供材料清单、甲控材料清单，辽宁省有关专业定额、政府结算文件，对竣工结算进行专业审查，成员企业工程负责人组织相关人员配合、协调。","审查期限：                                        1、500万元以下：从接到完整的拟建工程预算资料之日起20天                                                2、500-2000万：从接到完整的拟建工程预算资料之日起30天                              3、2000-5000万：从接到完整的拟建工程预算资料之日起45天                               4、5000万以上：从接到完整的拟建工程预算资料之日起60天",null,"集团专业预算采购主管"]
[6,"出具审查意见","E6","集团专业预算采购主管根据审查结果及征询成员企业工程负责人、承包单位意见，出具审查报告。","拟建工程预算审核完毕后1个工作日。","审查报告","集团专业预算采购主管"]
[7,"审 核","D7","集团预算采购高级主管根据集团公司预算管理制度审核专业预算采购主管审查报告","提交拟建工程预算审查报告后2个工作日。","审查报告","集团预算采购高级主管"]
[8,"审 核","C7","集团计财部长根据集团公司预算管理制度审核专业预算采购主管审查报告","提交拟建工程预算审查报告后1个工作日。","审查报告","集团计财部长"]
[9," 审查报告修订","B8","成员企业工程负责人对预算采购小组出具的审查报告组织修订","收到审查报告2个工作日。","审查报告","成员企业工程负责人"]
[10,"提出意见","A8","成员企业工程负责人对预算采购小组出具的审查报告修订后征求本企业CEO意见","报告修订后1个工作日。","审查报告","成员企业CEO"]
[11,"审 核","D9","集团预算采购高级主管根据集团公司预算管理制度审核成员企业工程负责人修订后审查报告","收到修订报告0.5个工作日.","审查报告","集团预算采购高级主管"]
[12,"审 核","C10","集团计财部长根据集团公司预算管理制度审核成员企业工程负责人修订后审查报告","收到修订报告0.5个工作日.","审查报告","集团计财部长"]
[13,"签批","C11","集团计财部长对审核的审查报告及预算书签字批准。","收到审核后审查报告及预算书0.5个工作日","审查报告","集团计财部长"]
[14,"存档","B12","成员企业工程负责人组织本企业综合部对竣工工程预算审查报告存档","预算审查报告存档3份（综合部1份、计财部1份、工程部1份），向工程承包单位发放1份、集团计财部预算采购小组发放1份","审查报告","成员企业工程负责人"]
[15,"存档","D12","集团预算采购高级主管组织竣工审查报告存档","预算审查报告存档1份","审查报告","集团预算采购高级主管"]
[16,"结束","D13",{"$nulls":3},"集团预算采购高级主管"]

{"sheet":"预算清单","index":2,"n_rows":13,"n_cols":5,"rows_kept":13,"merged":[[0,0,0,4],[1,0,1,1],[2,0,2,1],[3,0,8,1],[3,2,8,4],[9,0,9,1],[9,2,9,4],[10,0,10,1],[10,2,10,4],[11,0,11,1],[11,2,11,4],[12,0,12,3]],"flags":["formulas_cached_only"]}
["           拟建工程预算提交清单            编号："]
["成员企业名称",null,null,"成员企业部门"]
["项目名称",null,null,"工程名称"]
["本期提交拟建工程预算资料内容",null,"             提交人;                       日期："]
[]
[]
[]
[]
[]
["工程负责人意见",null,"                  工程负责人 :                      日期："]
["集团预算采购主管意见",null,"                 预算采购主管：                         日期："]
["集团预算采购高级主管审核意见",null,"             预算采购高级主管：                         日期："]
["清单编制人：",{"$nulls":3},"     编制日期："]

{"sheet":"拟建预算审查报告","index":3,"n_rows":14,"n_cols":5,"rows_kept":14,"merged":[[0,0,0,4],[1,0,1,1],[2,0,2,1],[3,0,3,1],[3,2,3,4],[4,0,9,1],[4,2,9,4],[10,0,10,1],[10,2,10,4],[11,0,11,1],[11,2,11,4],[12,0,12,1],[12,2,12,4],[13,0,13,3]],"flags":["formulas_cached_only"]}
["        拟建工程预算审查报告      编号："]
["拟建工程审查部门",null,null,"收到资料日期"]
["项目名称",null,null,"工程名称"]
["成员企业提供的相关资料"]
["本期审查完成内容",null,"    专业预算采购主管                       日期："]
[]
[]
[]
[]
[]
["集团专业预算采购主管本期审查意见",null,"           专业预算采购主管                       日期："]
["集团预算采购高级主管审核意见",null,"           集团预算采购高级主管：                 日期："]
["集团计财部部长审核意见",null,"           集团计财部长：                         日期："]
["报告编制人：",{"$nulls":3},"     编制日期："]